## Defect_tracker
SI No | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status (Open/Closed) | Remarks
1 | 2026-03-20 | Voice recognition getting aborted frequently | Sprint 1 | Backend Team | Functional | Added delay before starting mic and handled speech conflict | 2026-03-21 | Closed | Issue resolved after fix
2 | 2026-03-21 | Intent detection mismatch (PNR not working properly) | Sprint 1 | Backend Team | Logic | Unified intent naming across functions | 2026-03-22 | Closed | Working correctly now
3 | 2026-03-22 | Booking flow accepting same source and destination | Sprint 2 | Backend Team | Validation | Added check to prevent same source and destination | 2026-03-23 | Closed | Validated successfully
4 | 2026-03-23 | UI not displaying IVR responses properly | Sprint 2 | Frontend Team | UI/Integration | Fixed message rendering and formatting | 2026-03-24 | Closed | UI improved
5 | 2026-03-24 | Delay in API response during multiple requests | Sprint 2 | Backend Team | Performance | Optimized API handling and session management | 2026-03-25 | Closed | Response time improved
6 | 2026-03-25 | Voice input not mapping correctly to options | Sprint 3 | Frontend Team | Logic | Improved smart mapping logic for speech input | 2026-03-26 | Closed | Accuracy increased
7 | 2026-03-26 | Session expiring unexpectedly during interaction | Sprint 3 | Backend Team | Functional | Improved session handling logic | 2026-03-27 | Closed | Stable sessions
8 | 2026-03-27 | Train schedule not showing properly formatted output | Sprint 3 | Backend Team | UI/Logic | Improved formatting of schedule display | 2026-03-28 | Closed | Readable output
9 | 2026-03-28 | Seat availability showing incorrect data format | Sprint 4 | Backend Team | Functional | Updated response format for clarity | 2026-03-29 | Closed | Verified
10 | 2026-03-29 | Minor UI alignment issues in keypad and buttons | Sprint 4 | Frontend Team | UI | Fixed CSS alignment and layout | 2026-03-29 | Closed | UI polished